NAMA FOUNDATION  |  PRIME PROJECT MANAGEMENT COURSE

Project DPro Video Course Production Proposal

Updated proposal using Project DPro (PMD Pro 2nd Edition), while retaining the original 2017 course structure for management comparison.

01  Project Snapshot

| Item | Proposal |
| --- | --- |
| Project | PRIME - Project DPro / PMD Pro Project Management Video Course |
| Organization | NAMA Foundation |
| Purpose | Create a clear, practical, connected AI-avatar course that teaches learners how to manage a development or humanitarian project from identification and definition through closure. |
| Recommended content basis | 2020 Quick Guide to Project DPro as the course backbone; 2020 full Project DPro Guide (PMD Pro 2nd Edition) as the authoritative reference. |
| Previous content basis | 2017 PMD Pro Guide + old PMD Pro Starter, retained in this proposal for comparison and historical reference. |
| Recommended course size | 6 units, 14 lessons; each lesson 5-12 minutes; approximately 125-153 minutes total. |
| Teaching method | One continuous fictional NGO/development project is carried through the course so each tool and phase connects to the next. |

02  Learning & Video Direction

| Element | Direction |
| --- | --- |
| Target audience | Young professionals, development/humanitarian staff, project officers, coordinators, local implementing partners, volunteers moving into project roles, and early-stage project managers. |
| Tone | Warm, professional, practical and conversational. The avatar sounds like an experienced project practitioner guiding one learner, not like a lecturer reading a manual. |
| Language | Simple professional English. Project DPro terms are used when needed and explained in normal language. |
| Scene length | 30-45 seconds per scene. |
| Scene script | 600-800 characters including audio tags. Each scene completes one clear learning point before the transition. |
| Lesson flow | Where are we? -> Why is this needed? -> Explain the concept -> Show how it works -> Apply it to the same project -> Show the output -> Connect to the next lesson. |
| Visual theme | Modern Project Workflow: deep navy/indigo, white text, teal/warm accent, clean cards, diagrams, timelines and project-management visuals. |
| Recurring layouts | Presenter full-screen; presenter + visual; full-screen visual takeover; key-message card. |

03  Tools & Content Sources

| Tool / Source | Role in the workflow |
| --- | --- |
| Claude | Content mapping, lesson structure, script drafting, scene logic, continuity, visual planning, and final video editing: assembling avatar clips, diagrams/cards, subtitles, transitions and timing. |
| Google Vids | AI-avatar generation only. Locked scene scripts are turned into presenter/avatar clips; the final lesson is edited outside Google Vids through Claude. |
| 2020 Quick Guide to Project DPro | Recommended course backbone. It provides the concise updated lifecycle, core tools, principles and learning flow. |
| 2020 Full Project DPro Guide | Authoritative reference for accuracy, deeper explanation, examples and correct application of the methodology. |
| 2017 PMD Pro Guide + Starter | Retained only for comparison/reference so management can see what changed from the original proposal. |

04  What Changed from the 2017 Version

MANAGEMENT COMPARISON

2017 PMD Pro vs 2020 Project DPro

The 2020 edition keeps most of the core project-management concepts, but reorganizes the methodology and strengthens governance, MEAL, accountability and adaptive management. The course structures below are proposed video-learning designs based on the two source sets; they are not official PM4NGOs lesson structures.

| Area | 2017 PMD Pro Full Guide + Starter | 2020 Project DPro Full Guide + Quick Guide | What changed |
| --- | --- | --- | --- |
| Official framework | PMD Pro Full Guide, Version 1.9 (2017). The Starter is a simplified practical resource based on the same first-edition methodology. | Project DPro / PMD Pro 2nd Edition (2020). The Quick Guide summarizes the Second Edition. | PMD Pro was updated and rebranded as Project DPro. The core methodology remains, but its structure and presentation were revised. |
| Project lifecycle | 6 phases: Identification & Design; Setup; Planning; Implementation; Monitoring, Evaluation & Control; End-of-Project Transition. | 5 phases: Identification & Definition; Setup; Planning; Implementation; Closure. | The lifecycle was simplified and reorganized from six phases to five. |
| Monitoring, evaluation & learning | Monitoring, Evaluation & Control (MEC) is formally one of the six phases, although MEC activities continue throughout the project. | MEAL: Monitoring, Evaluation, Accountability & Learning is explicitly cross-cutting and incorporated into every phase. | Accountability and Learning were added, and MEAL is no longer presented as a separate phase. |
| Principles | Balanced, Comprehensive, Integrated, Participatory, Iterative. | Well-Governed, Participatory, Comprehensive, Integrated, Adaptive. | Balanced and Iterative were reframed through stronger emphasis on governance and adaptive management. |
| Disciplines / tools | Six disciplines are taught in a separate section: Scope, Time, Resources, Risk, Justification and Stakeholder Management. | The disciplines and their tools are integrated into the phases where they are actually used. | The updated structure creates a more lifecycle-based learning flow. |
| Governance & decisions | Governance structures and Decision Gates already exist in the old guide. | Governance, authority, tolerances and Decision Gates receive more explicit and systematic emphasis across the lifecycle. | Governance is not new; it is strengthened and more deeply integrated in the new edition. |
| Accountability & learning | Learning exists through monitoring/evaluation and end-of-project learning, but accountability and learning are less explicit as one cross-cutting framework. | Accountability and Learning are formally incorporated into MEAL and project decision-making. | They become more visible and systematic throughout the lifecycle. |
| Planning & adaptation | Iterative and rolling-wave planning are already included in the old methodology. | Rolling-wave planning, stage plans, the Adaptive principle, Decision Gates and controlled change receive stronger emphasis. | The change is mainly stronger integration and emphasis, rather than these concepts being completely new. |
| Sustainability & closure | The final phase is End-of-Project Transition, covering deliverables, learning and administrative, financial and contractual closure. | Sustainability and closure are considered from earlier phases, with sustainability planning, handover, reporting, evaluation and formal closure. | Closure is planned earlier and treated as part of the whole lifecycle rather than only an end activity. |
| Course structure | Our original proposal used 5 units / 12 lessons, primarily structured around the older materials and Starter tools. | Our recommended update uses 6 units / 14 lessons, following the 2020 lifecycle and integrated methodology. | These are proposed course structures, not official PM4NGOs lesson structures; the 2017 plan is retained only for comparison. |

Recommendation: Use the 2020 Quick Guide as the concise course backbone and the 2020 full Project DPro Guide as the authoritative reference for terminology, methodology and deeper explanations. Retain the 2017 course plan only for comparison.

ORIGINAL 2017 COURSE STRUCTURE - RETAINED FOR COMPARISON

Five Units, Twelve Connected Lessons

Original learning journey: Understand the problem -> design the solution -> authorize it -> plan the work -> manage implementation -> handle issues and change -> learn -> close.

| Unit | L# | Lesson | What it contains | Target |
| --- | --- | --- | --- | --- |
| Unit 1 - Foundations | 1 | Project Management & the PMD Pro Journey | Project basics, PMD Pro model, phases, principles, disciplines and project constraints. | 7-8 min |
| Unit 2 - Design | 2 | From Problems to Solutions | Problem Tree + Objective Tree: identify causes/effects, then turn them into solutions and objectives. | 9-10 min |
|  | 3 | Building the Project Logic | Logical Framework: activities, outputs, outcomes, goal, indicators, verification and assumptions. | 10-12 min |
|  | 4 | Authorizing the Project | Project Charter: purpose, scope, deliverables, high-level estimates, risks, tolerances and approval. | 6-7 min |
| Unit 3 - Planning | 5 | Breaking Down & Sequencing Work | WBS + Network Diagram: define the work, dependencies, sequence and critical path. | 9-11 min |
|  | 6 | Project Cost & Budget | Estimate costs, identify resources, build the budget and understand budget monitoring. | 7-8 min |
|  | 7 | Risk Management | Risk Register: identify, score, respond to and assign ownership for project risks. | 8-9 min |
|  | 8 | Project Scheduling | Gantt Chart: convert activities and dependencies into a usable project timeline. | 7-8 min |
| Unit 4 - Implementation & Control | 9 | Putting the Plan Together | Implementation Plan + RACI: combine the plan and clarify who is responsible, accountable, consulted and informed. | 9-10 min |
|  | 10 | Managing Problems & Changes | Issue Log + Change Control: record issues, resolve/escalate them and control changes to the approved plan. | 8-9 min |
| Unit 5 - Learn & Close | 11 | Learning from the Project | After Action Review: compare plan with reality, identify what worked, what did not and lessons for the future. | 6-7 min |
|  | 12 | Closing the Project | Deliverable acceptance plus contract, financial and administrative closure, records and handover. | 6-7 min |

Original-plan note: This structure reflects the 2017 PMD Pro/Starter logic. It is kept here for comparison and should not be treated as the preferred structure for new production.

RECOMMENDED 2020 COURSE STRUCTURE

Six Units, Fourteen Connected Lessons

Recommended learning journey: Understand Project DPro -> Identify & Define -> Set Up -> Plan -> Implement & Adapt -> Close & Learn.

Estimated total: approximately 125-153 minutes across 14 lessons, while keeping each lesson within the 5-12 minute target.

| Unit | L# | Lesson | What it contains | Target |
| --- | --- | --- | --- | --- |
| Unit 1 - Foundations | 1 | Understanding Project DPro | Project basics, development/humanitarian context, project vs program vs portfolio, Triple Constraint, 5 phases and the project manager role. | 8-10 min |
|  | 2 | How Project DPro Works Across the Lifecycle | Five principles, decision gates, overlapping phases and MEAL as a cross-cutting function. | 8-10 min |
| Unit 2 - Identification & Definition | 3 | Understanding the Need and the Context | Needs definition, data collection, qualitative/quantitative/secondary data, triangulation and stakeholder analysis. | 9-11 min |
|  | 4 | From Problems to Solutions | Current state, Problem Tree, future state, Objective Tree and deciding what is in or out of project scope. | 8-10 min |
|  | 5 | Building the Project Logic | Logframe: activities, outputs, outcomes, goal, indicators, means of verification, assumptions and SMART indicators. | 10-12 min |
|  | 6 | Shaping the Project Concept | High-level risk, HR, supply-chain, finance and sustainability analyses; Theory of Change alignment; proposal and draft charter. | 8-10 min |
| Unit 3 - Project Setup | 7 | Authorizing and Governing the Project | Final Project Charter, governance structure, authority, accountability, tolerances, decision-making and project launch. | 8-10 min |
|  | 8 | Preparing the Project for Planning | Comprehensive Risk Register, stakeholder engagement strategy, risk responses, planning framework and initial MEAL framework. | 9-11 min |
| Unit 4 - Project Planning | 9 | From Scope to Schedule | Scope of work, WBS, Network Diagram, resource/duration estimates, Critical Path and Gantt Chart. | 10-12 min |
|  | 10 | Building the Integrated Implementation Plan | Risk Plan, MEAL Plan, communications, stakeholder engagement, RACI, supply chain, HR and budget/resource planning. | 10-12 min |
|  | 11 | Planning for Change, Sustainability & Closure | Rolling-wave planning, stage plans, decision gates, sustainability, closure planning, internal controls and change-control preparation. | 8-10 min |
| Unit 5 - Project Implementation | 12 | Managing Delivery | Managing people, schedule, budget, risks and operational performance during implementation. | 9-11 min |
|  | 13 | Managing Issues, Change & Learning | Issue Log, change control, MEAL, accountability, stakeholder feedback, learning, supply chain and sustainability reviews. | 10-12 min |
| Unit 6 - Project Closure | 14 | Closing, Handover & Learning | Sustainability and handover, final reports, contract/financial/administrative closure, evaluation, lessons learned and After Action Review. | 10-12 min |

Why 14 lessons: The updated edition adds or strengthens needs/context analysis, stakeholder analysis, MEAL, governance, decision gates, adaptive planning and sustainability. These are important enough to teach clearly without overloading individual scenes.

05  How the Lessons Stay Connected

The whole course follows one fictional NGO/development project. Each lesson produces an output that becomes input for the next lesson. The updated chain is: needs/context + stakeholders -> Problem Tree -> Objective Tree -> Logframe -> project concept/proposal -> Charter + governance -> Risk/Stakeholder/MEAL setup -> WBS/Network/Critical Path/Gantt -> integrated Implementation Plan -> delivery + MEAL -> issues/change/adaptation -> sustainability, handover, evaluation and closure. This keeps the course as one project journey rather than a collection of unrelated tools.

Scene principle: One scene = one complete thought. A scene may combine closely related points, but it never explains half of a point and pushes the rest into the next scene.

PRESENTER & PRODUCTION

Avatar Options

Presenter direction: a realistic young-to-mid-career development-sector professional: calm, credible, friendly, practical, and comfortable moving between full-screen presentation and diagram-led explanation.

| LEO More senior/expert presence. Good if the course should feel formal and authoritative. | JAMES Young and approachable. Good if the course should feel especially friendly and youth-oriented. | WILLIAM Balanced, confident and approachable. Recommended because he fits both professional and development-sector training. |
| --- | --- | --- |
| JACK Warm, mentor-like presence. Good if the course should feel supportive, reflective and community-centered. | CALEB Experienced and approachable. Good if the course should feel credible, calm and professional without being overly formal. | SEBASTIAN Youthful and energetic. Good if the course should feel modern, accessible and especially relatable to younger professionals. |

06  Production Workflow

| Production step | What happens |
| --- | --- |
| 1. Content Map | Map the 2020 Quick Guide into the recommended 14-lesson journey, using the full 2020 Guide to verify depth, terminology and application. |
| 2. Script | Write scene-based avatar scripts: 600-800 characters, 30-45 seconds, one complete point per scene. |
| 3. Visual Plan | Assign each scene a visual mode: full avatar, split-screen, visual takeover or key-message card; specify diagrams, matrices, flows and cards before editing. |
| 4. Continuity Review | Check that every lesson starts from a previous output, answers one project-management need, and produces something useful for the next lesson. |
| 5. Google Vids Avatar Generation | Generate the AI-avatar presenter clips from the locked scene scripts. Google Vids is used for avatar generation only. |
| 6. Claude Video Editing | Claude assembles avatar clips, adds diagrams/cards, subtitles, transitions and timing, and keeps the visual theme consistent across all lessons. |
| 7. QA & Finalization | Review Project DPro accuracy, narration, scene completeness, transitions, visual clarity, timing and consistency before release. |

Production rule: Google Vids creates the avatar clips; Claude performs the final video editing and assembly. The scripts, visual plans and continuity checks are locked before production to reduce unclear scene transitions.